Project Planning Phase

Project Planning (Product Backlog, Sprint Planning, Stories, Story Points)

Heritage Treasures: An In-Depth Analysis of UNESCO World Heritage Sites (2019)

| Project Title | Heritage Treasures: An In-Depth Analysis of UNESCO World Heritage Sites (2019) |
| --- | --- |
| Domain | Culture & Heritage Analytics / Tourism & Conservation Business Intelligence |
| Tool | Tableau Desktop / Tableau Public |
| Dataset | Kaggle UNESCO World Heritage Sites Dataset, 1978–2019 (~1,121 sites, 12 fields) |
| Prepared By | M. Deepika (Team Lead), M. Supraja, K. Srikala, I. Pushpa, U. Bhavana |
| Mentor | Not yet assigned |
| GitHub Repository | https://github.com/mankudeepika123-rgb/Heritage-Treasures-An-In-Depth-Analysis-of-UNESCO-World-Heritage-Sites-2019- |
| Tableau Public Link | https://public.tableau.com/app/profile/manku.deepika5282/viz/HeritageTreasuresAnIn-DepthAnalysisofUNESCOWorldHeritageSites2019/UNESCOSiteOverviewDangerSitesAnalysis |
| Date | 22/08/2026 |

# 4.1 Product Backlog & Sprint Schedule

Tasks below are distributed across the 5-person team across 3 sprints.

| Epic # | Epic Name | User Story / Task | Story Points | Priority | Assigned To | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Data Collection | Download and review the Kaggle UNESCO World Heritage Sites dataset | 2 | High | M. Deepika | Sprint 1 |
| 1 | Data Collection | Confirm dataset fields: Category, Country, Region, Year Inscribed, Danger Status | 1 | High | M. Supraja | Sprint 1 |
| 2 | Data Preparation | Standardise Country and Region names; check for missing values | 3 | High | M. Deepika | Sprint 1 |
| 2 | Data Preparation | Set Country geographic role; verify no unmatched locations on the map | 2 | High | K. Srikala | Sprint 1 |
| 3 | Data Visualization | Build World map coloured by Danger Status | 3 | High | M. Supraja | Sprint 1 |
| 3 | Data Visualization | Build Category distribution chart (Cultural / Natural / Mixed) | 2 | High | I. Pushpa | Sprint 1 |
| 3 | Data Visualization | Build Region-wise Danger ranking chart | 2 | High | K. Srikala | Sprint 2 |
| 3 | Data Visualization | Build Inscription trend line chart (1978–2019) | 2 | Medium | I. Pushpa | Sprint 2 |
| 4 | Dashboard | Assemble Conservation Officer Dashboard (Map + Region ranking) | 3 | High | M. Deepika | Sprint 2 |
| 4 | Dashboard | Assemble Tourism Planner Dashboard (Map + Category chart) | 3 | High | M. Supraja | Sprint 2 |
| 4 | Dashboard | Assemble Policy Researcher Dashboard (Trend chart + Danger timeline) | 2 | Medium | K. Srikala | Sprint 2 |
| 5 | Story | Build Tableau Story with one story point per persona and captions | 3 | Medium | U. Bhavana | Sprint 3 |
| 6 | Performance Testing | Test all filters for responsiveness; document load time and data volume | 2 | Medium | M. Deepika | Sprint 3 |
| 7 | Web Integration | Publish workbook to Tableau Public; verify URL access | 2 | High | M. Supraja | Sprint 3 |
| 8 | Documentation | Complete all GitHub repository deliverables (docs, report, screenshots) | 5 | High | U. Bhavana | Sprint 3 |
| 8 | Documentation | Record project demonstration video | 3 | High | I. Pushpa | Sprint 3 |

Velocity Sprint 1 = 13 points | Sprint 2 = 15 points | Sprint 3 = 15 points | Total = 43 story points

Reading the Sprint Plan Sprint 1 focuses on data preparation and the first two core charts, since every later chart and dashboard depends on the Country/Region geographic model being set up correctly. Sprint 2 carries dashboard assembly, the heaviest integration work. Sprint 3 covers the Story, testing, and documentation — comparatively lighter but essential to a submission-ready deliverable.